## Delivery Schedule
CS692, Fall 2020 - Project Delivery Schedule
Tasks | 2020-08-28 | 2020-09-04 | 2020-09-11 | 2020-09-18 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-11-27 | 2020-12-04
Plan two releases (R1, R2) | Introduction to Project II | PLAN | PLAN | PLAN | [5 empty] | SPRING BREAK, NO CLASSES SCHEDULED | PASSOVER, NO CLASSES SCHEDULED | PASSOVER, NO CLASSES SCHEDULED |  | THANKSGIVINGG, NO CLASSES
MS1: Deliver Road Map |  |  |  | MS1
R1: Iteration 1 deliverables |  |  |  |  | I1: DEV + TEST
Agile: Workshop 1 | [5 empty] | WS1
Midterm Exam | [6 empty] | Exam MT
R1: Iteration 2 deliverables | [7 empty] | I2: DEV+TEST
MS2: R1 Project Presentation | [8 empty] | MS2
R2: Iteration 3 deliverables | [9 empty] | I3: DEV | I3: TEST
RUP: Workshop 2 | [10 empty] | WS2
R2: Iteration 4 deliverables | [11 empty] | I4: DEV |  |  | I4: TEST
Final Exam | [12 empty] | Exam Fin
MS3: R2 Project Presentation | [14 empty] | MS3
| Project Planning |  |  |  | R1: Agile Development |  |  |  |  | R2: RUP Development
[5 empty] | Agile: Iteration 1 |  |  | Agile: Iteration 2 |  | RUP: Elaboration |  | RUP: Construction

## R1 Checklist
Agile: R1 Project Checklist and Grading
No | Deliverables | Presented in Class | Owner Role | MAX Points
1 | R1: Road Map (I1, I2, Story Points, Velocity) | YES | Product Owner | 10
2 | R1: User Story Map (2nd tab in Road Map Excel) | NO | Product Owner | 5
3 | R1: Tasks for User Stories (using RCT) | NO | Project Manager | 7
4 | R1: Burn -down chart (for each iteration) | YES | Project Manager | 5
5 | R1: BRM Diagram | YES | Product Owner | 5
6 | R1: Context Diagram | YES | Lead BA | 5
7 | R1: RCT - Planning I1, I2 | YES | Lead BA | 7
8 | R1: User Stories (I1, I2) | YES | Product Owner | 10
9 | R1: Architecture Diagrams (3) | NO | Lead Developer | 5
10 | R1: ER Diagrams (conceptual, logical) | NO | DBA | 5
11 | R1: Source Code sample (part of Demo) + GitHub repository slides (images) | YES | Lead Developer | 5
12 | R1: Acceptance Tests (I1, I2) | YES | Lead QA | 8
13 | R1: Test Execution Log (I1, I2) | YES | Lead QA | 3
14 | R1: Application Demo | YES | Lead Developer | 20
|  |  | TOT: | 100

## R1 Presentation
Presentation Sequence | Presentation Documents | Presentation Instructions
1 | R1: Road Map (I1, I2, Story Points, Velocity) | Explain which user stories and why the team selected for I1 and I2 implementation. How the team assessed the Velocity Number for each iteration. | S
2 | R1: Burn -down chart (for each iteration) | Illustrate on Burn-down charts the team's progress implementing I1 and I2. | S
3 | BRM Diagram | Give a quick overview of the business model, explain if the model evolved through R1 cycle. | A
4 | Context Diagram | Give a quick overview of the context model, explain if the model evolved through R1 cycle. | Swe
5 | R1: Updated RCT (I1, I2) | Use only the iteration planning view of RCT, explain which crosscuts the team decided to implement in I1 and I2 and why. | WZ
6 | R1: User Stories (I1, I2) | Explain one of the user stories the team included in the live Demo. | Shivani
7 | R1: Acceptance Tests (I1, I2) | Explain one of the test design documents for the user story that will be in the application Demo. | A
8 | R1: Test Execution Log (I1, I2) | Explain the test execution log, provide evidence that the implemented functionality is stable. | Nishant
9 | GitHub "R1 Documents" | Open GitHub PowerPoint and show the repository structure and contents of the folder "R1 Documents". | ZS
10 | R1: Application Demo | The application Demo should be pre-recorded and include those user stories the team implemented in R1. | ZS

## WS1 Checklist
Agile I1: Workshop 1 Checklist
No | Deliverables | Presented in Class | Owner Role
1 | R1: Road Map (I1 Story Points, Velocity) | YES | Product Owner
2 | R1: User Story Map (2nd tab in Road Map Excel) | YES | Product Owner
3 | R1: Tasks for User Stories (using RCT) | NO | Project Manager
4 | R1: Burn -down chart (for each iteration) | YES | Project Manager
5 | R1: BRM Diagram | NO | Product Owner
6 | R1: Context Diagram | NO | Lead BA
7 | R1: RCT - Planning I1, I2 | YES | Lead BA
8 | R1: User Stories (I1) | YES | Product Owner
9 | R1: Architecture Diagrams (2) | NO | Lead Developer
10 | R1: ER Diagrams (conceptual, logical) | NO | DBA
11 | R1: Application + GitHub Demo | YES | Lead Developer
12 | R1: Acceptance Tests (I1) | YES | Lead QA
13 | R1: Test Execution Log (I1) | YES | Lead QA
14 | R1: Retrospective Report | YES | Lead Developer

## R1 Guidelines
Agile: R1 Project Checklist and Guidelines
Note, file names for all documents should be enumerated following the below list of deliverables. Examples: 4. R1_BRM_Team 2; 5. R1_Context Diagram_Team 2
No | Deliverables | Owner Role | Comments
1 | R1: Road Map (I1, I2, Story Points, Velocity) | Product Owner | 1. Follow the Road Map template on Blackboard. 2. The Road Map includes the entire product backlog (list of core features) allocated to R1 and R2 iterations. In R1 core features are user stories, in R2 core features are use cases. 3. All core features in the backlog should match the RCT core feature titles and ID. 4. Grey out those core features that the team already implemented last semester in Project I, do not allocate them to Project II iterations, do not count their story points. 5. Each user story (core feature), allocated to an iteration, should have a number (story points) representing the effort to implement the story. 6. For each iteration, include the Velocity number (SUM of story points). Make sure the Velocity numbers for I1 and I2 are comparable. 7. For each interation indicate the delivery date (see Delivery Schedule tab). Note - you do not need to allocate to iterations ALL features in the list, only those that the team can actually develop during this semester, so the plan should be realistic and practical. The features that you do not plan to implement do not need to be assigned story points.
2 | R1: Tasks for User Stories (using RCT) | Project Manager | 1. Identify tasks for all user stories in the scope of a given interation. 2. List of Tasks is a planning document that, for each user story, includes a list of DEVELOPMENT and TESTING tasks, task owners and Start/End dates. 3. Tasks should cover some crosscuts, i.e., those crosscuts you plan to implement for a given user story (refer to the RCT). 4. To identify tasks for a user story, check the RCT and see which crosscuts you included in R2 scope and plan to implement. Each crosscut should have at least one task. 5. See Slide 33 (Lecture W4) as a reference, also examples on Blackboard.
N/A | Weekly Quiz | All Team Members | 1. A project team creates a quiz on the topic of the last lecture; 2. Each team member creates ONE quiz question and sends it to the Project Manager; 3. The Project Manager collects quiz questions from all team members and sends the completed quiz to the Instructor. 4. The completed quiz is presented in a table with two columns - Student Name, Quiz Question. The document includes a header indicating the Quiz Topic.
3 | R1: Burn -down chart (I1, I2) | Project Manager | 1. Follow the example on Blackboard. 2. Each chart is developed for a given iteration. 3. The starting point in a chart represents the Velocity number from the Road Map (should match).
4 | BRM Diagram | Product Owner | 1. Follow the BRM template from the lecture material (W4, Slide 20). 2. The central part (internal organization structure) includes data flows among the internal groups. 3. The BRM business groups should match the list of stakeholders in the PID document. 4. If the internal organization structure includes multiple groups, highlight those groups, e.g., mark with an asterisk, that will be direct users of your application. 5. For each of these groups, identify user roles in a separate slide. 6. The diagram should be delivered in a Power Point document with a title on each slide.
5 | Context Diagram | Lead BA | 1. The diagram includes your system and external parties - external systems and main user roles. 2. For all external systems, the diagram shows data flows with labels indicating the type of data being exchanged. 3. When showing a user in the diagram, use a UML symbol "Actor" to differentiate it from a system. 4. The second slide includes a System Interface Table explaining external dataflows, see the lecture material (W4, Slide 34). 5. The diagram should be delivered in a Power Point document with a title on a slide. 6. If a diagram was changed from the previous semester, insert one more slide "Revision Notes" and indicate what is diffrenet.
6 | R1: User Roles (tab in Road Map) | Product Owner | 1. User Roles are specified in the form of a traceability table that is a separate tab in the Road Map document. 2. Each role can be traced to multiple features; the list of features should match the product backlog in the Road Map. 3. This table will be used for specifying user stories (R1) and use cases (R2).
7 | R1: Updated RCT (I1, I2) | Lead BA | 1. For R1 and R2, RCT is used as a planning document. 2. Using the original RCT, identify those core features that you allocated in Road Map to R1 (I1 and I2); mark the RCT cells for those features with I1 and I2 for the iterations 1 and 2 respectively. Important, you allocate to iterations only those crosscuts that the team plans to implement for I1 and I2. 3. Consistency check - verify that the information in the Road Map and RCT is consistent.
8 | R1: User Stories (I1, I2) | Product Owner | 1. Follow the template on Blackboard to capture User Stories. Note, the last column in the template includes "Story Constraints". 2. For each user story, check the Role Traceability table first to understand which roles (users) should be included in the story specification. 3. The stories you completed last semester mark "Last Semester", do not relate them to any iteration. 4. The stories you do not implement at all mark as TBD.
9 | R1: Architecture Diagrams (3) | Lead Developer | 1. Produce three architecture diagrams representing the following views - logical, process, and physical architecture views. 2. Include diagrams in a Power Point document, each slide should have a title: - architecture type - architecture view - architecture style (i.e. pattern name) 3. If any diagram was changed from the previous semester, insert one more slide "Revision Notes" and indicate what is diffrenet.
10 | R1: ER Diagrams (conceptual, logical) | DBA | 1. Conceptual database diagram includes the related business entities; its scope includes the entire data model; it is used for discussions with business stakeholders. 2. Logical ERD diagram includes data tables, and table fields. For each table we mark fields that are either primary or foreign keys. The scope of the Logical ERD reflects the scope of R1 implementation. 3. Include diagrams in a Power Point document, where each slide should have a title. 4. If a conceptual diagram was changed from the previous semester, insert one more slide "Revision Notes" and indicate what is diffrenet.
11 | R1: Source Code sample + GitHub repository slides (images) | Lead Developer | Capture the GitHub info in a PP doc (slides): - login info (first slide) and repository structure (other slides) - sample of your source code representing the feature that will be the focus of your project presentation. - slide with a build/deployment procedure
12 | R1: Acceptance Tests (I1, I2) | Lead QA | 1. Follow the template and guidelines on the Blackboard. 2. Each test document is produced for ONE core feature that is highlighted in the first tab RCT. 3. The test design tab identified the list of test cases, where the Core Feature and GUI tests are required. 4. In addition, you identify some crosscuts for this test design and mark the related cells in the RCT (first tab). When you design test cases for crosscuts, first please read a crosscut description in the original RCT. 5. Field Validation (FV) testing focuses ONE data entry field at a time. 6. To test Data Dependency (DDV). you need to produce a decision table, which will be the basis for test design.
13 | R1: Test Execution Log (I1, I2) | Lead QA | 1. Test execution log is captured in a separate Tab in the Excel template. 2. Test execution log includes ALL test cases you identified in the Test Design tab. 3. For each test case, you capture the execution status, execution date and tester's name.
14 | R1: Live Demo, class presentation | Lead Developer | 1. For the live Demo, you need to come to the class room and check in advance the laptop connectivity to the computer projector in the room. 2. For the class presentation, the team needs to rehearse the presentation flow, decide who is presenting which document. 3. For the presentation flow, the team identifies one core feature (user story) and presents and discusses the documents related to this core feature.

## R1 Detailed Schedule
Week | Class Date | CS692 Topics | Owner Role | Project Deliverables | Assigned to
1 | 2020-08-28 | Introduction to Project II
Project I - Selected Topics
2 | 2020-09-04 | Agile Software Requirements | Project Manager | Finalize project scope (R1 and R2); confirm project teams
3 | 2020-09-11 | Use-Case Modeling and Specification | Project Manager | R1: Road Map (includes 4 iterations)
|  |  | Product Owner | R1: User Story Map (second tab in Road Map Excel)
|  |  | Product Owner | BRM Diagram
|  |  | Lead BA | Context Diagram
|  |  | Lead Developer | Architecture Diagrams (3)
|  |  | All | Quiz - Agile Software Requirements
4 | 2020-09-18 | Aspect-Oriented Requirements | Product Owner | R1: Updated Road Map with Story Points (2 iterations)
|  |  | Lead BA | R1: Updated RCT with Iteration planning (2 iterations)
|  |  | All | Quiz - Use-Case Modeling
5 | 2020-09-25 | Mastering Test Design | Product Owner | R1: I1: User Stories | Anushree
|  |  | Project Manager | R1: I1: Tasks for User Stories | Siddharth, Ziteng
|  |  | Project Manager | R1: I1: Burn -down chart | Siddharth
|  |  | DBA | R1: I1: ER Diagrams (conceptual, logical) | Swetha
|  |  | Lead Developer | R1: I1: Source Code for User Stories (in GitHub repository) | Ziteng, Shivani
|  |  | Lead QA | R1: I1: Acceptance Tests | Anushree, Nishant
|  |  | Lead QA | R1: I1: Test Execution Log | Nishant
|  |  | All | Quiz - Aspect-Oriented Requirements
6 | 2020-10-02 | Agile: Hands-on Workshop 1; Exam preparation | Product Owner | R1: I1: User Stories | Anushree
| End of I1 |  | Project Manager | R1: I1: Tasks for User Stories | Siddharth, Ziteng
|  |  | Project Manager | R1: I1: Burn -down chart | Siddharth, Ziteng
|  |  | Lead Developer | R1: I1: Source Code for User Stories (real source code sample for archiving) + GitHub info in PP Slides | Ziteng, Shivani
|  |  | Lead QA | R1: I1: Acceptance Tests | Anushree
|  |  | Lead QA | R1: I1: Test Execution Log | Nishant Hulwan
|  |  | Project Manager | R1: I1: Retrospective Report | Shivani Gumpula
|  |  | All | Quiz - Mastering Test Design | All
7 | 2020-10-09 |  | Mid-Term Exam
8 | 2020-10-16 | Managing Iterative Projects | Product Owner | R1: I2: User Stories; Story Points | Anushree
|  |  | Project Manager | R1: I2: Tasks for User Stories | Siddharth, Ziteng
|  |  | Project Manager | R1: I2: Burn -down chart | Siddharth, Ziteng
|  |  | DBA | R1: I2: ER Diagrams (conceptual, logical) | Swetha
|  |  | Lead Developer | R1: I2: Source Code for User Stories | Ziteng, Shivani
|  |  | Lead QA | R1: I2: Acceptance Tests | Anushree, Weili
|  |  | Lead QA | R1: I2: Test Execution Log | Nishant Hulwan
9 | 2020-10-23 | Agile: R1 - Project Presentations | Product Owner | R1: I2: User Stories | Anushree
| End of I2 |  | Project Manager | R1: I2: Tasks for User Stories | Siddharth
|  |  | Project Manager | R1: I2: Burn -down chart | Siddharth
|  |  | Lead Developer | R1: I2: Source Code for User Stories (real source code sample for archiving) + GitHub info in PP Slides | Ziteng, Shivani
|  |  | Lead QA | R1: I2: Acceptance Tests | Anushree
|  |  | Lead QA | R1: I2: Test Execution Log | Nishant Hulwan
|  |  | Project Manager | R1: I2: Retrospective Report | Shivani Gumpula
|  |  | All | Quiz - Managing Iterative Projects
|  |  | Project Manager | R1: Send deliverables based on R1 Checklist to Class Instructor