## Road Map
BundleBid - Road Map
|  |  | Release 1 (Agile) |  | Release 2 (RUP)
RCT Modules | Feature Backlog | Story Points | I1 - 10-2-2020 | I2 - 10-22-2020 | I3 - 11-6-2020 | I4 - 11-20-2020
1. List a product | 01.01 Creating a Product | 5 | x
| 01.02 Modifying a Product | 3 | x
| 01.03 Deleting a Product | 2 | x
| 01.04 Listing History | 3 | x
2. User Account | 02.01 Register Account
02.02 Update Account
02.03 Close Account
| 02.04 Purchase/Bidding History | 2 |  | x
02.05 Sign in to Account
3. Browse for Products | 03.01 Search Product | 5 |  |  | x
| 03.02 Product Category | 2 |  |  | x
| 03.03 Product Subcategory | 2 |  |  | x
4. Bidding a Product | 04.01 Submit a Bid | 3 |  | x
| 04.02 Buy at Max Bid | 3 |  | x
5. Payment Gateway | 05.01 Send Payment Detail | 5 |  |  |  | x
| 05.02 Payment Verification | 3 |  |  |  | x
|  | VELOCITY: | 13 | 8 | 9 | 8
|  | RUP Phases: | Inception |  | Elaboration | Construction

## Story Map
Epics:
1. List a product | User Stories | BundleBid - User Story Map
2. User Account |  | 1. List a product | 2. User Account | 3. Browse for Products | 4. Bidding a Product | 5. Payment Gateway
3. Browse for Products |  | 01.01 Creating a Product
4. Bidding a Product |  | 01.02 Modifying a Product
5. Payment Gateway |  | 01.03 Deleting a Product
|  | 01.04 Listing History |  |  |  |  | Iteration 1
|  |  | 02.04 Purchase/Bidding History |  | 04.01 Submit a Bid
[5 empty] | 04.02 Buy at Max Bid |  | Iteration 2
03.01 Search Product
03.02 Product Category
|  |  |  | 03.03 Product Subcategory |  |  | Iteration 3
05.01 Send Payment Detail
[6 empty] | 05.02 Payment Verification | Iteration 4