## User Stories
USER STORIES: BundleBid
Modules | ID | Title | As a/an | I want to | so that | Itertions | Story Points | Story Constraints
1. List a product | 1.01 | Creating a Product | Online Wholesaler / Partner Relationship Manage | create a new listing for my product | list the new product I want to sell | I1 | 5 | Only registered wholesaler should be able to upload product(s) for sell.
| 1.02 | Modifying a Product | Online Wholesaler | change information on my product list | have correct information for the product I listed | I1 | 3 | Register wholesalers can modify the specifications of listed product(s); so that user of the website can have valid information about the product.
| 1.03 | Deleting a Product | Online Wholesaler / Partner Relationship Manager | remove products from my listed products | delete the item I no longer want to sell | I1 | 2 | Authorised used i.e. register wholesaler can remove the product(s) from the website, if he/she no longer wants to sell that item.
| 1.04 | Listing History | Online Wholesaler | access the history of item sold | see my sell's history | I1 | 3 | Register wholesaler should be able to view history of all sold items, to prepare plan for future uploading of products.
2. User Account | 2.01 | Registar Account | Online Wholesaler | register an account | have an registered account with BundleBid | Spring 2020 |  | If a new user wants to buy or sell any item from BundleBid website, then he or she must be a registered user.
| 2.02 | Update Account | Online Wholesaler / Online Buyer / Call Center Customer Support | update information for my account | have correct information on my account | Spring 2020 |  | To store as well as to display accurate information on user account, user should be able to modify his/her personal information.
| 2.03 | Close Account | Online Wholesaler / Online Buyer / Call Center Customer Support | remove my account | have my account permanently closed | Spring 2020 |  | Any time when user wants to close the account, he/she should be able to do that.
| 2.04 | Bidding History | Online Buyer / Call Center Customer Support | check what I have bid before | have access to my bid and purchase history | I2 | 2 | User should have access to all his/her previous biddings and purchase history.
| 2.05 | Sign in to account | Online Wholesaler / Online Buyer | sign in to my account | access my account | Spring 2020 |  | To purchase or to bid on a product, user should login to an account.
3.Browse for Products | 3.01 | Search a Product | Online Buyer / Advertisement Sales Representative / Advertising Manager | search a product on BundleBid | find a specific product I need | I3 | 5 | Registered as well as non-registered users should be able to search for the product(s) on website.
| 3.02 | Product Category | Online Buyer / Advertisement Sales Representative / Advertising Manager | search products in a specific category | see similar products in a category | I3 | 2 | Instead of searching from lists of products, user should be able to search within specific product categories such as clothing, cosmetics, etc.
| 3.03 | Product Subcategory | Online Buyer / Advertisement Sales Representative / Advertising Manager | narrow down searching on a more specific subcategory | see similar products that are in a more specific subcategory | I3 | 2 | User should be able to search for a product from respected product subcategory, to narrow down the searching task of user.
4. Bidding a Product | 4.01 | Submit a bid | Online Buyer / Advertisement Sales Representative / Advertising Manager | submit a bid on a product | send in my bidding price for a specific product | I2 | 3 | User should be able to submit valid bid on a product(s).
| 4.02 | Buy at max bid | Online Buyer / Advertisement Sales Representative / Advertising Manager | submit a max bid on a product | bid out the product right away at max bid setted by the seller | I2 | 3 | If user submitted a maximum bid as compare to others, then he or she should be redirected to payment gateway.
5.Payment Gateway | 5.01 | Send Payment Detail | Online Wholesaler / Online Buyer | transfer my payment information | send out my payment information so that I can complete the bidding | I4 | 5 | As user submits a maximum bid, system should provide payment details to user.
| 5.02 | Payment Verification | Online Wholesaler / Delivery Manager / Accountant / Account Coordinator | confirm a payment is completed | mark the payment is verified and completed | I4 | 3 | Once user done with the payment process, system should provide an acknowledgment in the form of bill or invoice.
Iteration 1 (I1)
Iteration 2 (I2)
Iteration 3 (I3)
Iteration 4 (I4)
Implemented in Spring 2020

## User Roles
User Role | Description
Partner Relationship Manager | Partner Relationship Manager is responsible for stock management purpose. The person will co-ordinate with local suppliers and wholesalers to fulfill the user's demands.
Advertisement Sales Representative/ Advertising Manager | Advertisement Sales Representative or manager are associated with the advertising departments. They are responsible fo doing an advertisement for products in order to attract more customers.
Delivery Manager | Delivery Manager is associated with Delivery Management depatment and is responsible for handeling all the delivery operations.
Accountant | Accountant is associated with Account depatment and is responsible for handeling financial activities such as providing payment details, processing user payments, providing acknowledgement, etc.
Account Co-ordinator/Call Center Customer Support | Account co-ordinator is in customer support team and is responsible for ensuring theat customers are satisfied at all the times. This person is also responsible for maintaining user account with the accurate information.