## Tasks List - R1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner | Iteration
1 | 01. List a product | 01. 01 | Creating a Product | Implement GUI based changes to site | 9-19-2020 | 9-21-2020 | 100% | Shivani Gumpala | I1
2 | 01. List a product | 01. 01 | Creating a Product | Add back-end support to functions | 9-19-2020 | 9-21-2020 | 100% | Ziteng Sun | I1
3 | 01. List a product | 01. 01 | Creating a Product | Implement crosscutting concerns - CS, DDV, FV, DDD, DFI, DFO, CN | 9-19-2020 | 9-21-2020 | 100% | Ziteng Sun, Swetha Bitla | I1
4 | 01. List a product | 01. 01 | Creating a Product | Assign Test cases for the core features | 9-22-2020 | 9-23-2020 | 0% | Anushree Khopkar | I1
5 | 01. List a product | 01. 01 | Creating a Product | Test scripts and report results | 9-23-2020 | 9-24-2020 | 0% | Nishant Hulwan | I1
6 | 01. List a product | 01. 04 | Listing History | Implement GUI based changes to site | 9-19-2020 | 9-21-2020 | 0% | Shivani Gumpala | I1
7 | 01. List a product | 01. 04 | Listing History | Add back-end support to functions | 9-19-2020 | 9-21-2020 | 0% | Ziteng Sun | I1
8 | 01. List a product | 01. 04 | Listing History | Implement crosscutting concerns - CS, DDD, DDV, DFI, CN | 9-19-2020 | 9-21-2020 | 0% | Ziteng Sun, Swetha Bitla | I1
9 | 01. List a product | 01. 04 | Listing History | Assign Test cases for the core features | 9-22-2020 | 9-23-2020 | 0% | Anushree Khopkar | I1
10 | 01. List a product | 01. 04 | Listing History | Test scripts and report results | 9-23-2020 | 9-24-2020 | 0% | Weili Zhong | I1
11 | 01. List a product | 01. 03 | Deleting a Product | Add delete option to listing history | 9-26-2020 | 9-28-2020 | 0% | Shivani Gumpala | I1
12 | 01. List a product | 01. 03 | Deleting a Product | Add back-end support to option | 9-26-2020 | 9-28-2020 | 0% | Ziteng Sun | I1
13 | 01. List a product | 01. 03 | Deleting a Product | Implement crosscutting concerns - CS, DDV, FV, DDD, DFI, DFO, CN | 9-26-2020 | 9-28-2020 | 0% | Ziteng Sun, Swetha Bitla | I1
14 | 01. List a product | 01. 03 | Deleting a Product | Assign Test cases for the core features | 9-29-2020 | 9-30-2020 | 0% | Anushree Khopkar | I1
15 | 01. List a product | 01. 03 | Deleting a Product | Test scripts and report results | 9-30-2020 | 2020-01-10 | 0% | Nishant Hulwan | I1
16 | 01. List a product | 01. 02 | Modifying a Product | Implement crosscutting concerns - CS, DDV, FV, DDD, DFI, DFO, CN | 9-26-2020 | 9-28-2020 | 0% | Shivani Gumpala | I1
17 | 01. List a product | 01. 03 | Modifying a Product | Add back-end support to form | 9-26-2020 | 9-28-2020 | 0% | Ziteng Sun | I1
18 | 01. List a product | 01. 04 | Modifying a Product | Implement crosscutting concerns | 9-26-2020 | 9-28-2020 | 0% | Ziteng Sun, Swetha Bitla | I1
19 | 01. List a product | 01. 05 | Modifying a Product | Assign Test cases for the core features | 9-29-2020 | 9-30-2020 | 0% | Anushree Khopkar | I1
20 | 01. List a product | 01. 06 | Modifying a Product | Test scripts and report results | 9-30-2020 | 2020-01-10 | 0% | Nishant Hulwan | I1
21 | 0.2. User Account | 02. 04 | Purchase/Bidding History | Add user info options and Add history to the database | 2020-09-10 | 2020-12-10 | 0% | Shivani Gumpala, Ziteng Sun | I2
22 | 0.2. User Account | 02. 04 | Purchase/Bidding History | Implement crosscutting concerns - CS, DFI, DFO |  |  | 0% | Ziteng Sun | I2
23 | 0.2. User Account | 02. 04 | Purchase/Bidding History | Assign Test cases for the core features |  |  | 0% | Anushree Khopkar | I2
24 | 0.2. User Account | 02. 04 | Purchase/Bidding History | Test scripts and report results |  |  | 0% | Weili Zhong | I2
25 | 0.4. Bidding a Product | 04. 01 | Submit a Bid | Add bidding buttons | 2020-09-10 | 2020-11-10 | 0% | Shivani Gumpala | I2
26 | 0.4. Bidding a Product | 04. 01 | Submit a Bid | Add back-end support for bidding | 2020-10-10 | 2020-12-10 | 0% | Ziteng Sun | I2
27 | 0.4. Bidding a Product | 04. 01 | Submit a Bid | Implement crosscutting concerns - CS, DDV, FV, DDD, DFI, DFO, CN | 2020-10-10 | 2020-12-10 | 0% | Swetha Bitla | I2
28 | 0.4. Bidding a Product | 04. 01 | Submit a Bid | Assign Test cases for the core features | 10-13-2020 | 10-15-2020 | 0% | Anushree Khopkar | I2
29 | 0.4. Bidding a Product | 04. 01 | Submit a Bid | Test scripts and report results |  |  | 0% | Nishant Hulwan | I2
30 | 0.4. Bidding a Product | 04. 02 | Buy at Max Bid | Add button for Max Bid to products which support it | 2020-09-10 | 2020-11-10 | 0% | Shivani Gumpala | I2
31 | 0.4. Bidding a Product | 04. 02 | Buy at Max Bid | Add back-end support to enable buyout at MaxBid | 2020-10-10 | 2020-12-10 | 0% | Ziteng Sun | I2
32 | 0.4. Bidding a Product | 04. 02 | Buy at Max Bid | Implement crosscutting concerns - CS, DDV, FV, DDD, DFI, DFO | 2020-10-10 | 2020-12-10 | 0% | Swetha Bitla | I2
33 | 0.4. Bidding a Product | 04. 02 | Buy at Max Bid | Assign Test cases for the core features | 10-13-2020 | 10-15-2020 | 0% | Anushree Khopkar | I2
34 | 0.4. Bidding a Product | 04. 02 | Buy at Max Bid | Test scripts and report results |  |  | 0% | Nishant Hulwan | I2

## Tasks List - R2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner | Iteration
1 | 0.3. Browse for Products | 03. 01 | Search Product | Implement GUI based search bar |  |  | 0% | Shivani Gumpala | I3
2 | 0.3. Browse for Products | 03. 01 | Search Product | Add back-end support to bar |  |  | 0% | Ziteng Sun | I3
3 | 0.3. Browse for Products | 03. 01 | Search Product | Confirm database support |  |  | 0% | Swetha Bitla | I3
4 | 0.3. Browse for Products | 03. 01 | Search Product | Assign Test cases for the core features |  |  | 0% | Anushree Khopkar | I3
5 | 0.3. Browse for Products | 03. 01 | Search Product | Test scripts and report results |  |  | 0% | Nishant Hulwan | I3
6 | 0.3. Browse for Products | 03. 02 | Product Category | Implement GUI based Navigation bars |  |  | 0% | Shivani Gumpala | I3
7 | 0.3. Browse for Products | 03. 02 | Product Category | Connect nav-bar to categories |  |  | 0% | Ziteng Sun | I3
8 | 0.3. Browse for Products | 03. 02 | Product Category | Confirm database support |  |  | 0% | Swetha Bitla | I3
9 | 0.3. Browse for Products | 03. 02 | Product Category | Assign Test cases for the core features |  |  | 0% | Anushree Khopkar | I3
10 | 0.3. Browse for Products | 03. 02 | Product Category | Test scripts and report results |  |  | 0% | Nishant Hulwan | I3
11 | 0.3. Browse for Products | 03. 03 | Product Subcategory | Display sub-categories based on selected category |  |  | 0% | Shivani Gumpala | I3
12 | 0.3. Browse for Products | 03. 03 | Product Subcategory | Add back-end support to functions |  |  | 0% | Ziteng Sun | I3
13 | 0.3. Browse for Products | 03. 03 | Product Subcategory | Confirm database support |  |  | 0% | Swetha Bitla | I3
14 | 0.3. Browse for Products | 03. 03 | Product Subcategory | Assign Test cases for the core features |  |  | 0% | Anushree Khopkar | I3
15 | 0.3. Browse for Products | 03. 03 | Product Subcategory | Test scripts and report results |  |  | 0% | Nishant Hulwan | I3
16 | 0.5. Payment Gateway | 05. 01 | Send Payment Detail | Implement GUI based changes to site |  |  | 0% | Shivani Gumpala | I4
17 | 0.5. Payment Gateway | 05. 01 | Send Payment Detail | Add back-end support to functions |  |  | 0% | Ziteng Sun | I4
18 | 0.5. Payment Gateway | 05. 01 | Send Payment Detail | Confirm database support |  |  | 0% | Swetha Bitla | I4
19 | 0.5. Payment Gateway | 05. 01 | Send Payment Detail | Assign Test cases for the core features |  |  | 0% | Anushree Khopkar | I4
20 | 0.5. Payment Gateway | 05. 01 | Send Payment Detail | Test scripts and report results |  |  | 0% | Nishant Hulwan | I4
21 | 0.5. Payment Gateway | 05. 02 | Payment Verification | Implement GUI based changes to site |  |  | 0% | Shivani Gumpala | I4
22 | 0.5. Payment Gateway | 05. 02 | Payment Verification | Add back-end support to functions |  |  | 0% | Ziteng Sun | I4
23 | 0.5. Payment Gateway | 05. 02 | Payment Verification | Confirm database support |  |  | 0% | Swetha Bitla | I4
24 | 0.5. Payment Gateway | 05. 02 | Payment Verification | Assign Test cases for the core features |  |  | 0% | Anushree Khopkar | I4
25 | 0.5. Payment Gateway | 05. 02 | Payment Verification | Test scripts and report results |  |  | 0% | Nishant Hulwan | I4