## Delivery Schedule
CS692, Fall 2020 - Project Delivery Schedule
Tasks | 2020-08-28 | 2020-09-04 | 2020-09-11 | 2020-09-18 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-11-27 | 2020-12-04
Plan two releases (R1, R2) | Introduction to Project II | PLAN | PLAN | PLAN | [5 empty] | SPRING BREAK, NO CLASSES SCHEDULED | PASSOVER, NO CLASSES SCHEDULED | PASSOVER, NO CLASSES SCHEDULED |  | THANKSGIVINGG, NO CLASSES
MS1: Deliver Road Map |  |  |  | MS1
R1: Iteration 1 deliverables |  |  |  |  | I1: DEV + TEST
Agile: Workshop 1 | [5 empty] | WS1
Midterm Exam | [6 empty] | Exam MT
R1: Iteration 2 deliverables | [7 empty] | I2: DEV+TEST
MS2: R1 Project Presentation | [8 empty] | MS2
R2: Iteration 3 deliverables | [9 empty] | I3: DEV | I3: TEST
RUP: Workshop 2 | [10 empty] | WS2
R2: Iteration 4 deliverables | [11 empty] | I4: DEV |  |  | I4: TEST
Final Exam | [12 empty] | Exam Fin
MS3: R2 Project Presentation | [14 empty] | MS3
| Project Planning |  |  |  | R1: Agile Development |  |  |  |  | R2: RUP Development
[5 empty] | Agile: Iteration 1 |  |  | Agile: Iteration 2 |  | RUP: Elaboration |  | RUP: Construction

## R2 Checlkist
R2 - Deliverables and Grades
No | Deliverables | Presented in Class | Owner Role | MAX Points
1 | R2: Road Map (I3, I4) | YES | Project Manager | 10
2 | R2: RCT - Planning I3, I4 | YES | Lead BA | 7
3 | R2: Actors Specification (ET Tab in RCT) | YES | Product Owner | 5
4 | R2: List of Tasks (using RCT) | NO | Project Manager | 7
5 | R2: Use-Case Diagrams (I3, I4) | YES | Lead BA | 5
6 | R2: UML Diagrams (Class, Sequence) | NO | Lead Developer | 5
7 | R2: Use-Case Specifications (with join points) | YES | Lead BA | 12
8 | R2: Supplementary Requirements | NO | Lead BA | 8
9 | R2: ER Diagrams (conceptual, logical) | NO | DBA | 5
10 | R1: Source Code sample (part of Demo) + GitHub repository slides (images) | NO | Lead Developer | 5
11 | R2: Functional Tests (I3, I4) | YES | Lead QA | 8
12 | R2: Test Execution Log (I3, I4) | YES | Lead QA | 3
13 | R2: Live Demo, Class Presentation | YES | Lead Developer | 20
|  |  | TOT: | 100

## R2 Presentation
Presentation Sequence | Presentation Documents | Presentation Instructions
1 | R2: Road Map (I3, I4) | Explain which use cases and why the team selected for I3 and I4 implementation. How the team assessed the Velocity Number for each iteration.
2 | R2: RCT - Planning I3, I4 | Use only the iteration planning view of the RCT, explain which crosscuts the team decided to implement in I3 and I4 and why.
3 | R2: Actors (ET Tab in RCT) | Give an overview of Actors and how you mapped them to use cases.
4 | R2: Use-Case Diagrams (I3, I4) | Give a quick overview of one diagram, explain what is represents.
5 | R2: Use-Case Specifications (with join points) | Explain one use case specification that will be in the application Demo. Explain how you incerted crosscuts using join points.
6 | R2: Functional Tests (I3, I4) | Explain one of the test design documents for the use case that will be in the application Demo.
7 | R2: Test Execution Log (I3, I4) | Explain the test execution log, provide evidence that the implemented R2 functionality is stable.
8 | GitHub "R2 Documents" | Open GitHub PowerPoint and show the repository structure and contents of the folder "R2 Documents".
9 | R1: Application Demo | The application Demo should be pre-recorded and include those use cases the team implemented in R2.

## WS2 Checklist
R2:I3 - Workshop Checklist
No | Deliverables | Presented in Class | Owner Role
1 | R2: Road Map (I3) | YES | Project Manager
2 | R2: RCT - Planning I3, I4 | YES | Lead BA
3 | R2: Actors Specification (ET Tab in RCT) | YES | Product Owner
4 | R2: List of Tasks (using RCT) | NO | Project Manager
5 | R2: Use-Case Diagram | YES | Lead BA
6 | R2: UML Diagrams (Class, Sequence) | NO | Lead Developer
7 | R2: Use-Case Specifications (with join points) | YES | Lead BA
8 | R2: Supplementary Requirements | YES | Lead BA
9 | R2: ER Diagrams (conceptual, logical) | NO | DBA
10 | R1: Application + GitHub repository demo | NO | Lead Developer
11 | R2: Functional Tests (I3) | YES | Lead QA
12 | R2: Test Execution Log (I3) | YES | Lead QA
13 | R2: Live Demo, class presentation | YES | Lead Developer

## R2 Guidelines
R2 - Deliverables and Guidelines
Note, file names for all documents should be enumerated following the below list of deliverables. Examples: 5. R2_Use Case Diagram_Team 2; 8. R2_Supplementary Requirements_Team 2
No | Deliverables | Owner Role | Comments
1 | R2: Road Map (I3, I4) | Project Manager | 1. Follow the Road Map template on Blackboard. 2. The Road Map includes the entire product backlog (list of core features) allocated to R2 iterations. In R1 core features are user stories, in R2 core features are use cases. 3. All core features in the backlog should match the RCT core feature titles and ID. 4. Each use case, allocated to an iteration, should have a number (story points) representing the effort to implement the use case. 5. For each iteration, include the Velocity number (SUM of story points). Make sure the Velocity numbers for I3 and I4 are comparable.
2 | R2: RCT - Planning I3, I4 | Lead BA | 1. For R1 and R2, RCT is used as a planning document. 2. Using the original RCT, identify those core features that you allocated in Road Map to R2 (I3 and I4); mark the RCT cells for those features with I3 and I4 for the iterations 3 and 4 respectively. Also, mark only those crosscuts that the team plans to implement for R2. 3. Consistency check - verify that the information in the Road Map and RCT is consistent.
3 | R2: Actors (Tab in RCT) | Product Owner | 1. Actors are specified in the form of a traceability table that is a separate tab in the RCT document. 2. Each Actor role can be traced to multiple features (use cases); the list of features should match the product backlog in the RCT. 3. This table will be used for specifying R2 use cases.
4 | R2: List of Tasks (using RCT) | Project Manager | 1. Identify tasks for all use cases in the scope of a given interation. 2. List of Tasks is a planning document that, for each use case, includes a list of DEVELOPMENT and TESTING tasks, task owners and Start/End dates. 3. Tasks should cover some crosscuts, i.e., those crosscuts you plan to implement for a given use case (refer to the RCT). 4. To identify tasks for a use case, check the RCT and see which crosscuts you included in R2 scope and plan to implement. Each crosscut should have at least one task. 5. See Slide 33 (Lecture W4) as a reference, also examples on Blackboard.
5 | R2: Use-Case Diagram | Lead BA | 1. Produce two use case diagrams - one for I3 and another one for I4. 2. Each use case diagram shows a group of related use cases and their actors that are in the scope of Iteration 3 and Iteration 4, use the UML Actor symbol to represent actors. 3. Include diagrams in a Power Point document, where each slide has a title.
6 | R2: UML Diagrams (Class, Sequence) | Lead Developer | 1. UML diagrams are produced for a specific use case that the team included in the scope of a given iteration. 2. Diagrams are delivered in a Power Point document, where each slide has a title, indicating which use case the diagram represents. 3. Sequence diagrams begin with the Actor, use the UML Actor symbol to represent actors. | UML Actor Symbol
7 | R2: Use-Case Specifications (with join points) | Lead BA | 1. Follow the use case template available on Blackboard. 2. Actors should match the User Roles in the traceability table in the Road Map. 3. Before you start writing a use case specification, review the guidelines in Lecture W3 (slides 41, 51). 4. The Use Case specification document should include all use cases - in scope of I3 and I4. 5. In a given use case, a Use Case scenario should include Join Points for all applicable crosscuts (refer to the RCT).
8 | R2: Supplementary Requirements | Lead BA | 1. Capture Supplementary Requirements in a Word document. 2. Before you start writing the Supplementary Requirements, review the lecture notes - W4, where Slide 48 shows the 3-part template for crosscut specifications: - scope - requirement - condition to apply 3. To decide which supplementary requirements to capture, review the RCT Planning document and check what you marked for implementation, also review the test design document and decide which crosscuts will be in scope of the test design. Then the supplementary requirements should be used as a test basis. 4. Note - do not include Entitlements in this document, you specified this requirement in the ET table in the RoadMap. 5. If you want to specify DF-In or DF-Out crosscuts, include a Dataflow diagram illustrating this requirement.
9 | R2: ER Diagrams (conceptual, logical) | DBA | 1. Conceptual database diagram includes the related business entities; its scope includes the entire data model; it is used for discussions with business stakeholders. 2. Logical ERD diagram includes data tables, and table fields. For each table we mark fields that are either primary or foreign keys. The scope of the Logical ERD reflects the scope of R2 implementation. 3. Include diagrams in a Power Point document, where each slide should have a title.
10 | R1: Source Code sample + GitHub repository slides (images) | Lead Developer | Capture the GitHub info in a PP doc (slides): - login info (first slide) and repository structure (other slides) - sample of your source code representing the feature that will be the focus of your project presentation. - slide with a build/deployment procedure
11 | R2: Functional Tests (I3, I4) | Lead QA | 1. Follow the template and guidelines on the Blackboard. 2. Each test document is produced for ONE core feature that is highlighted in the first tab RCT. 3. The test design tab identified the list of test cases, where the Core Feature and GUI tests are required. 4. In addition, you identify some crosscuts for this test design and mark the related cells in the RCT (first tab). When you design test cases for crosscuts, first please read a crosscut description in the original RCT. 5. To produce test case specifications for crosscuts, you need to produce a Supplementary Requirements document first that will provide the basis for test design. 6. Field Validation (FV) testing focuses ONE data entry field at a time. 7. To test Data Dependency (DDV), you need to produce a decision table, which will be the basis for test design.
12 | R2: Test Execution Log (I3, I4) | Lead QA | 1. Test execution log includes ALL test cases you identified in the Test Design tab. 2. For each test case, you capture the execution status, execution date and tester's name.
13 | R2: Live Demo, class presentation | Lead Developer | 1. For the live Demo, you need to come to the class room and check in advance the laptop connectivity to the computer projector in the room. 2. For the class presentation, the team needs to rehearse the presentation flow, decide who is presenting which document. 3. For the presentation flow, the team identifies one core feature (use case) and presents and discusses the documents related to this core feature.

## R2 Detailed Schedule
Week | Class Date | CS692 Topics | Owner Role | Project Deliverables
10 | 2020-10-30 | Configuration and Release Management | Project Manager | R2: Road Map (includes I3, I4 iterations) | S
|  |  | Lead BA | R2: Updated RCT (planning I3, I4 iterations) | W
|  |  | Product Owner | R2: Actors (Entitlements specification, Tab in RCT) | W
|  |  | Project Manager | R2: List of Tasks for I3 and I4 (using RCT) | S
|  |  | Lead BA | R2: I3: Use-Case Diagrams | A
|  |  | Lead BA | R2: I3: Use-Case Specifications | A
|  |  | Lead BA | R2: I3: Supplementary Requirements | Sh
|  |  | Lead Developer | R2: I3: UML Diagrams (Class, Sequence) | Sw
|  |  | DBA | R2: I3: ER Diagrams (conceptual, logical) | Sw
11 | 2020-11-06 | RUP: Workshop 2 | Lead Developer | R2: I3: Source Code for Use Cases (real source code sample for archiving) + GitHub info in PP Slides
| End of I3 |  | Lead QA | R2: Road Map (includes I3, I4 iterations) | S
|  |  | Lead QA | R2: Updated RCT (planning I3, I4 iterations) | S
|  |  | Lead QA | R2: Actors (Entitlements specification, Tab in RCT) | S
|  |  | Lead QA | R2: I3: Use-Case Diagrams | A
|  |  | Lead QA | R2: I3: Use-Case Specifications | A
|  |  | Lead QA | R2: I3: Functional Tests | A
|  |  | Lead QA | R2: I3: Test Execution Log | W
|  |  | Project Manager | R2: I3: Retrospective Report | Sh
|  |  | All | Quiz - Configuration and Release Management
12 | 2020-11-20 | Exam and R2 presentation preparations |  | R2: I4: Use-Case Diagrams
|  |  | Lead BA | R2: I4: Use-Case Specifications
|  |  | Lead BA | R2: I4: Supplementary Requirements
|  |  | Lead Developer | R2: I4: UML Diagrams (Class, Sequence)
|  |  | DBA | R2: I4: ER Diagrams (conceptual, logical)
13 | 2020-11-20 | Final Exam
| 2020-11-27 | THANKSGIVING, NO CLASSES
14 | 2020-12-04 | RUP: R2 - Project Presentations | Lead Developer | R2: I4: Source Code for Use Cases (real source code sample for archiving) + GitHub info in PP Slides
| End of I4 |  | Lead QA | R2: I4: Functional Tests
|  |  | Lead QA | R2: I4: Test Execution Log
|  |  | Project Manager | R2: I4: Retrospective Report
|  |  | Project Manager | R2: Send Deliverables based on R2 Checklist to Instructor