## Initial Plan
Color Coding |  | Completed |  |  |  | SPRING 2018 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-03-31 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-04-28 | 2020-05-05
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2020-01-28 | 2020-01-28 | 0%
| Confirm Project Team Roles | ALL | 2020-01-28 | 2020-01-28 | 0%
| Develop two business cases | Ziteng Sun, Nishant Hulwan | 2020-01-29 | 2020-02-04 | 0%
| Develop Project Initiation Document (PID) | Siddharth Jhaveri | 2020-02-05 | 2019-02-11 | 0%
| Produce initial Project Plan, RACI | Siddharth Jhaveri | 2020-02-12 | 2019-02-18 | 0%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Swetha Bitla | 2020-02-19 | 2020-02-25 | 0%
| Produce Context Diagram, Define System Interfaces | Anushree Khopkar | 2020-02-19 | 2020-02-25 | 0%
| Define Business Requirements | Shivani Gumpula | 2020-02-19 | 2020-02-25 | 0%
| Agree to System Requirements types | All | 2020-02-19 | 2020-02-25 | 0%
| Define Functional Decomposition | All | 2020-02-26 | 2020-03-03 | 0%
| Produce RCT document | Shivani Gumpula | 2020-02-26 | 2020-03-03 | 0%
| Decide which features to implement this semester | All | 2018-03-04 | 2020-03-10 | 0%
| Produce analysis diagrams (UML, DFD) | Shivani Gumpula | 2018-03-04 | 2020-03-10 | 0%
| Define functional requirements (User Stories) | Shivani Gumpula | 2018-03-04 | 2020-03-10 | 0%
| Update Project Plan with additional requirements tasks | Siddharth Jhaveri | 2018-03-04 | 2020-03-10 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Ziteng Sun | 2020-03-25 | 2020-03-31 | 0%
| Database Design (ERD, Table spec) | Anushree Khopkar | 2020-03-25 | 2020-03-31 | 0%
| System Interface Design | Ziteng Sun | 2020-04-01 | 2020-04-07 | 0%
| User interface design | Shivani Gumpula | 2020-04-01 | 2020-04-07 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | Ziteng Sun | 2020-04-08 | 2020-04-14 | 0%
| Coding & Implemenation | Ziteng Sun | 2020-04-08 | 2020-04-14 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Nishant Hulwan | 2020-04-15 | 2020-04-21 | 0%
| Evaluate Features to be Tested | Nishant Hulwan | 2020-04-15 | 2020-04-21 | 0%
| Design Test Cases | Nishant Hulwan | 2020-04-15 | 2020-04-21 | 0%
| Execute Test Cases | Nishant Hulwan | 2020-04-15 | 2020-04-21 | 0%
| Anaylze Test Results | ALL | 2020-04-15 | 2020-04-21 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2020-05-05 | 2020-05-05 | 0%

## Final Plan
Color Coding |  |  | Completed |  |  |  | SPRING 2020 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-03-31 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-04-28 | 2020-05-05
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2020-01-28 | 2020-01-28 | 100%
| Confirm Project Team Roles |  | ALL | 2020-01-28 | 2020-01-28 | 100%
| Develop two business cases |  | Ziteng Sun, Nishant Hulwan | 2020-01-29 | 2020-02-04 | 100%
| Develop Project Initiation Document (PID) |  | Siddharth Jhaveri | 2020-02-05 | 2019-02-11 | 100%
| Produce initial Project Plan, RACI |  | Siddharth Jhaveri | 2020-02-12 | 2019-02-18 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Anushree Khopkar | 2020-02-19 | 2020-02-25 | 100%
| Produce Context Diagram, Define System Interfaces |  | Shivani Gumpula | 2020-02-19 | 2020-02-25 | 100%
| Risk Management Strategy |  | Ziteng Son | 2020-02-19 | 2020-02-25 | 100%
| Define Business Requirements |  | Shivani Gumpula | 2020-02-26 | 2020-03-03 | 100%
| Agree to System Requirements types |  | Shivani Gumpula | 2020-02-26 | 2020-03-03 | 100%
| Define Functional Decomposition |  | Siddharth Jhaveri | 2020-02-26 | 2020-03-03 | 100%
| Produce RCT document |  | Ziteng Sun, Nishant Hulwan, Weili Zhong | 2020-02-26 | 2020-03-03 | 100%
| Decide which features to implement this semester |  | All | 2018-03-04 | 2020-03-10 | 100%
| Produce analysis diagrams (UML, DFD (Logical)) |  | Swetha Bitla, Anushree Khopkar | 2018-03-04 | 2020-03-10 | 100%
| Define functional requirements (User Stories) |  | Ziteng Sun | 2018-03-04 | 2020-03-10 | 100%
| Update Project Plan with additional requirements tasks |  | Siddharth Jhaveri | 2018-03-04 | 2020-03-10 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | ER Diagrams (Conceptual & Logical) |  | Swetha Bitla | 2020-03-17 | 2020-03-24 | 100%
| DFD (Physical) |  | Anushree Khopkar | 2020-03-17 | 2020-03-24 | 100%
| Database Specifications Table |  | Siddharth Jhaveri | 2020-03-17 | 2020-03-24 | 100%
| Architectural Diagrams |  | Ziteng Sun | 2020-03-24 | 2020-03-31 | 100%
| Class Diagram |  | Anushree Khopkar | 2020-04-01 | 2020-04-07 | 100%
| Sequence Diagram |  | Nishant Hulwan | 2020-04-01 | 2020-04-07 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Login Page | 02.01 Register Account | Ziteng Sun & Shivani Gumpula | 2020-04-01 | 2020-04-28 | 100%
|  | 02.02 Update Account |  | 2020-04-01 | 2020-04-28 | 100%
|  | 02.05 Sign in to Account |  | 2020-04-01 | 2020-04-28 | 100%
| Product Page | GUI & Functionality Design | Ziteng Sun & Shivani Gumpula | 2020-04-01 | 2020-04-21 | 100%
|  | Coding |  | 2020-04-01 | 2020-04-21 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Testing Table Document |  | Swetha Bitla, Weili Zhong | 2020-04-07 | 2020-04-14 | 100%
| Test Scripts and Cases |  | Anushree Khopkar | 2020-04-14 | 28_Apr | 100%
| Login Page | Design Test Cases | Anushree Khopkar | 2020-04-14 | 28_Apr | 100%
|  | Execute Test Cases | Anushree Khopkar | 2020-04-14 | 28_Apr | 100%
|  | Analyze Test Cases | Siddharth Jhaveri | 2020-04-14 | 28_Apr | 100%
| Product Page | Design Test Cases | Anushree Khopkar | 2020-04-14 | 21_Apr | 100%
|  | Execute Test Cases | Anushree Khopkar | 2020-04-14 | 21_Apr | 100%
|  | Analyze Test Cases | Siddharth Jhaveri | 2020-04-14 | 21_Apr | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2020-05-05 | 2020-05-05 | 100%